## Slide 1: Event Organisation - Risk Mitigation
Katjuša Koler
May 2019

## Slide 2: Overview
Organising an event
What could go wrong?
How can we mitigate it?
Notes: Examples of all the events

## Slide 3: Organising an event
Goals
Audience
Type of event
Budget
Location
Date & Time
Outputs and outcomes
Notes: Pictures of things

## Slide 4: Organising an event: Example
Goals
Audience
Type of event
Budget
Location
Date & Time
Outputs and outcomes
What could go wrong?
Discuss effective communication strategies with non-technical researchers
30 Research-Software Engineers
One-day workshop
£500
Sheffield University workroom
17th September 2019
Summary blog post
Notes: “Approaches for effective communication with non-technical researchers”

## Slide 5: Workshop goals
Produce guidelines on how to effectively communicate with non-technical researchers
Networking
Community growth
Continuing professional development
Reputational goals for the university

## Slide 6: What could go wrong?
BEFORE | DURING | AFTER
Not getting interest from target audience | Not accessible | Negative feedback
Sponsors dropping out | Additional dietary requirements | No feedback
Venue cancellation | Catering not arriving | Report of harassment
Organiser taking unexpected break | Allergy reactions | Sponsor money not clearing
Venue catering restrictions | Attendee unexpectedly ill | No volunteers for next year
Unachievable goals | Speaker not arriving (on time/right location) | Unforeseen expenses
No speaker | Under delivering to sponsors | Overspending
Lack of diversity in organisational team | Low attrition rate | Unsatisfied sponsors
Competing event date clash | Excluded attendees | Data breach
Not meeting budget goals | Not meeting advertised goals | No evidence of success
… | … | …

## Slide 7: How can we mitigate it?
Planning
  Identifying risks
  Risk Probability and Impact Assessment
  Risk Mitigation
 |  | Impact x Probability = Risk |  | 
Probability | High | Medium | High | Very high
 | Medium | Low | Medium | High
 | Low | Low | Low | Medium
 |  | Low | Medium | High
 |  | Impact |  | 

## Slide 8: Mitigation Strategies
  Avoid
  Limit/Mitigate
  Transfer
  Accept
Barron & Barron, 2011. Project Management for Scientists and Engineers
Notes: Risk Management Options Illustration from Barron & Barron Project Management for Scientists and Engineers, http://cnx.org/content/col11120/1.4/

## Slide 9: Before
Higher probability and impact
Risks mostly “invisible” to attendees
Avoidable by planning and maintaining flexibility
 | Risk | Strategy | Mitigation Plan
Competing event clash | High | Avoid | Change date
Not meeting budget goals | High | Limit/Transfer | Create min viable budget
Impact x Probability = Risk |  |  |  | 
Probability | H | Med | High | Very high
 | M | Low | Med | High
 | L | Low | Low | Med
 |  | L | M | H
 |  | Impact |  | 
Drawn from A. Watt, Risk Management Planning
Notes: bpayne and A. Watt, Risk Management Planning https://opentextbc.ca/projectmanagement/chapter/chapter-16-risk-management-planning-project-management/ Accessed May 14th 2019

## Slide 10: During
Attendee associated unforeseen risks
Risks mostly visible to attendees
Affects the attendee experience
Most avoidable by planning and maintaining flexibility
 | Risk | Strategy | Mitigation Plan
Fire at venue | Medium | Limit | Brief about fire exits
Participant feeling unwell | Low | Limit/Accept | Quiet room, support
Impact x Probability = Risk |  |  |  | 
Probability | H | Med | High | Very high
 | M | Low | Med | High
 | L | Low | Low | Med
 |  | L | M | H
 |  | Impact |  | 
Drawn from A. Watt, Risk Management Planning

## Slide 11: After
Harder to mitigate
Long-lasting impact
Timely response essential
Limit with informed processes before and during e.g. Code of conduct
 | Risk | Strategy | Mitigation Plan
Reported verbal harassment | Medium | Limit | Code of conduct
Publicly negative blog post | Low | Accept | Learn & improve
Impact x Probability = Risk |  |  |  | 
Probability | H | Med | High | Very high
 | M | Low | Med | High
 | L | Low | Low | Med
 |  | L | M | H
 |  | Impact |  | 
Drawn from A. Watt, Risk Management Planning

## Slide 12
Before:
Competing event clash
Not raising enough money
During:
Fire at venue
Participant feeling unwell
After:
Reported verbal harassment
Publicly negative blog post
 | Risk | Strategy | Mitigation Plan
 | High | Avoid | Change date
 | High | Limit/Transfer | Create min viable budget
 | Medium | Limit | Brief about fire exits
 | Low | Limit/Accept | Quiet room
 | Medium | Limit | Code of conduct
 | Low | Accept | Try better next time

## Slide 13: Take homes
A lot of things that can go wrong
Planning can mitigate most
Need a robust and informed process
  e.g. Promoting code of conduct and then reporting on it
Communication is key when things go wrong
  Effective problem resolution
  Attendee expectation management
Easier with great teamwork!